## Instructions
(1) Project Timeline (Row 2): Grant projects are limited to 18 months in length. The Schedule template assumes awarded projects will be contracted in January 2016 and be completed by June 2017. For the purposes of the application, all applicants MUST base their timeline on an January 2016 start date. If a proposed project is expected to be completed prior to June 2017, the remaining columns should be left blank. Once grant funds are awarded, the Schedule can be reconfigured based on actual start and end dates. The Schedule is divided into quarters.
(2) Grant Drawdown (Rows 3 & 4): Applicants MUST estimate the amount of Grant funds they will spend each quarter as well as the remaining grant fund percentage. The “Initial” column indicates that no grant funds can be expended prior to the contract execution date, and the “Final” column indicates that by the end of 6 quarters all grants funds are expected to be spent. Please note that the both the grant dollar amount (Row 3) and the percentage remaining (Row 4) must be entered manually into each cell.
(3) Match Expenditures (Rows 6 & 7 and 9 & 10): Applicants must also estimate the rate at which they expect to accrue match dollars. The “Initial” column indicates that no match funds can be accrued prior to the contract execution date, and the “Final” column indicates that by the end of 6 quarters, 100 percent of the match commitment will be met. Please note that both the match dollar amount (Row 6) and the percentage accrued (Row 7) must be entered manually into each cell. The cash amount applied as match (Row 9) and the percent accrued (Row 10) must be entered manualy.
(4) Contract Execution: This section has already been completed in the Template, and should remain as is.
(5) Tasks: Applicants should include all tasks from Section 5. (Project Activites) Task numbers should remain the same. It may be appropriate to shorten the task title to fit within the allotted space, but the intent of the task should remain clear. Applicants should “fill-in” the appropriate number of cells, creating a line that depicts the expected length of each task in months (tasks that will require less than one month should be represented by the filling in of an entire cell). Applicants are encouraged to color code their tasks by suitable categories. For instance, in the “Example Schedule”, meetings are color coded in purple and tasks that will result in deliverables to GAEPD are color coded in orange. A key should be provided.
(6) State Reporting Requirements: Grant recipients are required to submit Quarterly Reports and Invoices every three months for the length of the project to ensure adherence to the Implementation and Drawdown Schedule and to proactively address any concerns in a timely manner. These reporting requirements have already been completed in the Template (color coded in pink) and should remain as they are.
(7) Contract Close-Out: This section has already been completed in the Template, and should remain as is. The contract close-out date can be readjusted as necessary once grant funds are awarded.

## Example
Section 9: Implementation and Drawdown Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | Final
Grant Drawdown Amount | 0 | 5000 |  |  | 20000 |  |  | 22000 |  |  | 15000 |  |  | 8000 |  |  | 5000 |  |  | 75000
Percent Federal Remaing | 100% | 93.33% |  |  | 66.67% |  |  | 37.33% |  |  | 17.33% |  |  | 6.667% |  |  | 0% |  |  | 0%
Match Amount | 0 | 3000 |  |  | 10000 |  |  | 15000 |  |  | 10000 |  |  | 4000 |  |  | 3000 |  |  | 45000
Percent Match Accrued | 0% | 6.667% |  |  | 28.89% |  |  | 62.22% |  |  | 84.44% |  |  | 93.33% |  |  | 100% |  |  | 100%
|  | Jan 2016 | Feb 2016 | Mar 2016 | Apr 2016 | May 2016 | Jun 2016 | Jul 2016 | Aug 2016 | Sep 2016 | Oct 2016 | Nov 2016 | Dec 2016 | Jan 2017 | Feb 2017 | Mar 2017 | Apr 2017 | May 2017 | Jun 2017
Cash Match Amount | $0 | 1000 |  |  | 1000 |  |  | 1000 |  |  | 1000 |  |  | 1000 |  |  | 0 |  |  | 5000
Percent Cash Match Accrued | 0% | 20% |  |  | 40% |  |  | 60% |  |  | 80% |  |  | 100% |  |  | 100% |  |  | 100%
Milestones/Tasks
Execute Contract
Task 1:
Task 2:
Task 3:
Task 4: Conduct Public Meeting
Task 5:
Task 6:
Task 7:
Task 8: Conduct Public Outreach Day
Task 9: Submit Monitoring Data
Submit Quarterly Invoices & Status Reports
Submit Final Close-Out Report

## Template
Section 9: Implementation and Drawdown Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | Final
Grant Drawdown Amount | 0
Percent Federal Remaing | 100% | [18 empty] | 0%
Match Amount | 0
Percent Match Accrued | 0% | [18 empty] | 0%
Cash Match Amount | $0
Percent Cash Match Accrued | 0% | [18 empty] | 0%
|  | Jan 2016 | Feb 2016 | Mar 2016 | Apr 2016 | May 2016 | Jun 2016 | Jul 2016 | Aug 2016 | Sep 2016 | Oct 2016 | Nov 2016 | Dec 2016 | Jan 2017 | Feb 2017 | Mar 2017 | Apr 2017 | May 2017 | Jun 2017
Milestones/Tasks
Execute Contract
Task 1:
Task 2:
Task 3:
Task 4:
Task 5:
Task 6:
Task 7:
Task 8:
Task 9:
Task 10:
Task 11:
Task 12:
Task 13:
Task 14:
Task 15:
Submit Quarterly Invoices & Status Reports
Submit Final Close-Out Report