## Instructions
(1) Project Timeline (Row 2): Grant projects are limited to 30 months in length. For the purposes of the application, all applicants should base their timeline on an January 2023 start date. Once grant funds are awarded, the Schedule can be reconfigured based on actual start and end dates. The Schedule is divided into quarters.
(2) Grant Drawdown (Rows 3 & 4): Applicants must estimate the amount of Grant funds they will spend each quarter as well as the remaining grant fund percentage. The “Initial” column indicates that no grant funds can be expended prior to the contract execution date, and the “Final” column indicates that by the end, all grants funds are expected to be spent. Please note that the both the grant dollar amount (Row 3) and the percentage remaining (Row 4) must be entered manually into each cell.
(3) Match Expenditures (Rows 6 & 7 and 9 & 10): Applicants must also estimate the rate at which they expect to accrue match dollars. The “Initial” column indicates that no match funds can be accrued prior to the contract execution date, and the “Final” column indicates that by the end, 100 percent of the match commitment will be met. Please note that both the match dollar amount (Row 6) and the percentage accrued (Row 7) must be entered manually into each cell. The cash amount applied as match (Row 9) and the percent accrued (Row 10) must be entered manualy.
(4) Contract Execution: This section has already been completed in the Template, and should remain as is.
(5) Tasks: Applicants should include all tasks from Section 5. (Project Activites) Task numbers should remain the same. It may be appropriate to shorten the task title to fit within the allotted space, but the intent of the task should remain clear. Applicants should “fill-in” the appropriate number of cells, creating a line that depicts the expected length of each task in months (tasks that will require less than one month should be represented by the filling in of an entire cell). Applicants are encouraged to color code their tasks by suitable categories. For instance, in the “Example Schedule”, meetings are color coded in purple and tasks that will result in deliverables to GAEPD are color coded in orange. A key should be provided.
(6) State Reporting Requirements: Grant recipients are required to submit Quarterly Reports and Invoices every three months for the length of the project to ensure adherence to the Implementation and Drawdown Schedule and to proactively address any concerns in a timely manner. These reporting requirements have already been completed in the Template (color coded in pink) and should remain as they are.
(7) Contract Close-Out: This section has already been completed in the Template, and should remain as is. The contract close-out date can be readjusted as necessary once grant funds are awarded.

## Example
Appendix B: Project Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | Final
Grant Drawdown Amount | 0 | 5000 |  |  | 20000 |  |  | 22000 |  |  | 15000 |  |  | 8000 |  |  | 5000 |  |  | 75000
Percent Federal Remaining | 100% | 93.33% |  |  | 66.67% |  |  | 37.33% |  |  | 17.33% |  |  | 6.667% |  |  | 0% |  |  | 0%
Match Amount | 0 | 3000 |  |  | 5000 |  |  | 13500 |  |  | 10000 |  |  | 3000 |  |  | 3000 |  |  | 37500
Percent Match Accrued | 0% | 8% |  |  | 21.33% |  |  | 57.33% |  |  | 84% |  |  | 92% |  |  | 100% |  |  | 100%
Cash Match Amount | $0 | 2000 |  |  | 2000 |  |  | 1500 |  |  | 2500 |  |  | 3000 |  |  | 1500 |  |  | 12500
Percent Cash Match Accrued | 0% | 16% |  |  | 32% |  |  | 44% |  |  | 64% |  |  | 88% |  |  | 100% |  |  | 100%
|  | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01
Milestones/Tasks
Execute Contract
Task 1: | bar: 2023-01-01 to 2023-03-01
Task 2: | bar: 2023-04-01
Task 3: | bar: 2023-05-01 to 2023-06-01
Task 4: Conduct Public Meeting | bar: 2023-06-01
Task 5: | bar: 2023-07-01 to 2023-08-01
Task 6: | bar: 2023-09-01 to 2023-10-01
Task 7: | bar: 2023-11-01 to 2024-04-01
Task 8: Conduct Public Outreach Day | bar: 2024-05-01
Task 9: Submit Monitoring Data | bar: 2024-06-01
Submit Quarterly Invoices & Status Reports | bar: 2023-04-01; 2023-07-01; 2023-10-01; 2024-01-01; 2024-04-01
Submit Final Close-Out Report

## Template
Appendix B: Project Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | 7th Quarter |  |  | 8th Quarter |  |  | 9th Quarter |  |  | 10th Quarter |  |  | Final
Grant Drawdown Amount | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 75000 |  |  | 75000
Percent Seed Remaining | 100% | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 100% |  |  | 0% |  |  | 0%
Match Amount | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 37500 |  |  | 37500
Percent Match Accrued | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100%
Cash Match Amount | $0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 12500 |  |  | 12500
Percent Cash Match Accrued | 0% | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 100% |  |  | 100%
|  | Jan 2023 | Feb 2023 | Mar 2023 | Apr 2023 | May 2023 | Jun 2023 | Jul 2023 | Aug 2023 | Sep 2023 | Oct 2023 | Nov 2023 | Dec 2023 | Jan 2024 | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025
Milestones/Tasks
Execute Contract
Task 1:
Task 2:
Task 3:
Task 4:
Task 5:
Task 6:
Task 7:
Task 8:
Task 9:
Submit Quarterly Invoices & Status Reports
Submit Final Close-Out Report