## Instructions
(1) Project Timeline (Row 2): 319(h) projects are limited to 3 years in length. The Schedule Template assumes awarded projects will be contracted in October 2021 and be completed by September 2024. For the purposes of the application, all applicants MUST base their timeline on an October 2021 start date. If a proposed project is expected to be completed prior to September 2024, the remaining columns should be left blank. Once grant funds are awarded, the Schedule can be reconfigured based on actual start and end dates. The Schedule is divided into quarters that are numbered sequentially in order to track activities for the entire term of the project.
(2) Federal Drawdown Amount & Percent Federal Remaining (Rows 3 & 4): Applicants MUST estimate the amount of 319(h) Grant federal funds that they will spend each quarter (Row 3 - light blue) in order to calculate the percent of federal funds remaining (Row 4). The “Initial” column indicates the total amount of grant funds to be expended and the “Final” column indicates that by the end of 12 quarters all grant funds have been spent, resulting in $0 remaining. Please note that the grant dollar amount must be entered manually into each cell in Row 3 in order for the formulas in Row 4 to automatically calculate the percent remaining.
(3) Match Amount & Percent Match Accrued (Rows 6 & 7): Applicants must also estimate the match in dollar amounts that they expect to accrue each quarter (Row 6 - light yellow) in order to calculate the percent of match accrued (Row 7). The “Initial” column indicates that no match funds have been accrued prior to the contract execution date, and the “Final” column indicates that by the end of 12 quarters, 100 percent of the match commitment will be met. Please note that the match dollar amount must be entered manually into each cell in Row 6 in order for the formulas in Row 7 to automatically calculate the percent accrued.
(4) Contract Execution: This section has already been completed in the Template, and should remain as is.
(5) Tasks: Applicants should include all tasks from Section 5. Task numbers should remain the same. It may be appropriate to shorten the task title to fit within the allotted space, but the intent of the task should remain clear. Applicants should “fill-in” the appropriate number of cells, creating a line that depicts the expected length of each task in months (tasks that will require less than one month should be represented by the filling in of an entire cell). Applicants are encouraged to color code their tasks by suitable categories. For instance, in the “Example Schedule”, Meetings & Outreach are color coded in purple and tasks related to Urban BMPs are color coded in orange. A key should be provided.
(6) Federal/State Reporting Requirements: 319(h) Grant recipients are required to submit Quarterly Reports and Invoices every three months, as well as an Annual Report each October for the length of the project to ensure adherence to the Project Schedule and to proactively address any concerns in a timely manner. These reporting requirements have already been completed in the Template (color coded in pink) and should remain as they are.
(7) Contract Close-Out: This section has already been completed in the Template, and should remain as is. The contract close-out date can be readjusted as necessary once grant funds are awarded.
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed the 319(h) Project tab to Schedule Template to match what its called in Instructions
Note on A3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added refernce to the color row here abd below
Note on A9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed the worksheet tab that said "Example Implement WBP" to "Example Schedule" which its referred too here in the instrucations. Also changed the example color code text to match the actual Example Schedule.
Note on A11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added reference to Annual report here and added the Annual report row to the Example Schedule

## Example Schedule
Section 10: Project Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | 7th Quarter |  |  | 8th Quarter |  |  | 9th Quarter |  |  | 10th Quarter |  |  | 11th Quarter |  |  | 12th Quarter |  |  | Final
Federal Drawdown Amount | 209877 | 5000 |  |  | 5000 |  |  | 10000 |  |  | 10000 |  |  | 10000 |  |  | 15000 |  |  | 15000 |  |  | 40000 |  |  | 40000 |  |  | 20000 |  |  | 18889 |  |  | 20988 |  |  | 0
Percent Federal Remaining | 100% | 97.62% |  |  | 95.24% |  |  | 90.47% |  |  | 85.71% |  |  | 80.94% |  |  | 73.79% |  |  | 66.65% |  |  | 47.59% |  |  | 28.53% |  |  | 19% |  |  | 10% |  |  | -4.163e-15% |  |  | 0%
Match Amount | 0 | 3333 |  |  | 3333 |  |  | 6667 |  |  | 6667 |  |  | 6667 |  |  | 10000 |  |  | 10000 |  |  | 26667 |  |  | 26667 |  |  | 22107 |  |  | 12593 |  |  | 13992 |  |  | 148693
Percent Match Accrued | 0% | 2.242% |  |  | 4.483% |  |  | 8.967% |  |  | 13.45% |  |  | 17.93% |  |  | 24.66% |  |  | 31.38% |  |  | 49.32% |  |  | 67.25% |  |  | 82.12% |  |  | 90.59% |  |  | 100% |  |  | 100%
|  | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01
Milestones/Tasks
Execute Contract | bar: 2021-10-01
Task 1: Introduce Project to Watershed Partners | bar: 2021-12-01 to 2022-01-01
Task 2: Convene 3 Meetings to Assign Implementation Responsibilities | bar: 2022-03-01 to 2022-04-01; 2022-06-01 to 2022-07-01; 2022-09-01 to 2022-10-01
Task 3: Recruit & Contract with Ag Producers for Ag BMPs | bar: 2022-04-01 to 2023-09-01; 2024-01-01 to 2024-03-01
Task 4: Install Ag BMPs | bar: 2022-10-01 to 2024-06-01
Task 5: Recruit & Contract with Property Owners for Septic BMPs | bar: 2022-04-01 to 2023-09-01; 2024-01-01 to 2024-03-01
Task 6: Pump Out, Repair or Replace Septic Systems | bar: 2022-10-01 to 2024-06-01
Task 7: Recruit & Contract with Local Gov, Biz, or Institution for Urban BMP | bar: 2022-04-01 to 2023-09-01
Task 8: Install Green Infrastructure stormwater BMPs in Urban Watershed | bar: 2022-10-01 to 2024-06-01
Task 9: Conduct 2 BMP Workshops or Field Days | bar: 2023-06-01 to 2023-08-01; 2024-02-01 to 2024-04-01
Task 10: Estimate load reductions for sediment, phosphorus & nitrogen | bar: 2023-01-01; 2023-04-01; 2023-07-01; 2023-10-01; 2024-01-01; 2024-04-01; 2024-07-01
Task 11: Submit Quarterly Invoices & Status Reports | bar: 2022-04-01; 2022-07-01; 2023-01-01; 2023-04-01; 2023-07-01; 2024-01-01; 2024-04-01; 2024-07-01
Task 12: Submit Annual Report & Quarterly Invoice | bar: 2022-10-01; 2023-10-01
Task 13: Submit Final Close-Out Report & Invoice
Key
Meetings & Outreach
Ag BMPs
Septic BMPs
Urban BMPs
Contract & Reports

## Schedule Template
10. Project Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | 7th Quarter |  |  | 8th Quarter |  |  | 9th Quarter |  |  | 10th Quarter |  |  | 11th Quarter |  |  | 12th Quarter |  |  | Final
Federal Drawdown Amount | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Percent Federal Remaining | 100% | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | 0%
Match Amount | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Percent Match Accrued | 0% | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | 100%
|  | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01
Milestones/Tasks
Execute Contract | bar: 2021-10-01
Task 1:
Task 2:
Task 3:
Task 4:
Task 5:
Task 6:
Task 7:
Task 8:
Task 9:
Task 10:
Task 11:
Task 12:
Task 13:
Task 14:
Task 15:
Task 16:
Task 17:
Task 18:
Task 19:
Task 20:
Task 21:
Task 22:
Task 23:
Task 24: Submit Quarterly Invoices & Status Reports | bar: 2022-01-01; 2022-04-01; 2022-07-01; 2023-01-01; 2023-04-01; 2023-07-01; 2024-01-01; 2024-04-01; 2024-07-01
Task 25: Submit Annual Report & Quarterly Invoice | bar: 2022-10-01; 2023-10-01
Task 26: Submit Final Close-Out Report | bar: 2024-09-01
Key
Meetings & Outreach
Ag BMPs
Septic BMPs
Urban BMPs
Contract & Reports