## Instructions
Use the Project Schedule Template tab to create a schedule for the FY2024 project application. Do not use the Example Schedule tab.
(1) Project Timeline (Row 2): 319(h) projects are limited to 3 years in length. The Project Schedule Template assumes awarded projects will be contracted in July 2024 and be completed by June 2027. For the purposes of the application, all applicants MUST base their timeline on an July 2024 start date. If a proposed project is expected to be completed prior to June 2027, the remaining columns should be left blank. Once grant funds are awarded, the Schedule can be reconfigured based on actual start and end dates. The Schedule is divided into quarters that are numbered sequentially in order to track activities for the entire term of the project.
(2) Federal Drawdown Amount & Percent Federal Remaining (Rows 3 & 4): Applicants MUST estimate the amount of 319(h) Grant federal funds that they will spend each quarter (Row 3 - light blue) in order to calculate the percent of federal funds remaining (Row 4). The “Initial” column indicates the total amount of grant funds to be expended and the “Final” column indicates that by the end of 12 quarters all grant funds have been spent, resulting in $0 remaining. Please note that the grant dollar amount must be entered manually into each cell in Row 3 in order for the formulas in Row 4 to automatically calculate the percent remaining.
(3) Match Amount & Percent Match Accrued (Rows 6 & 7): Applicants must also estimate the match in dollar amounts that they expect to accrue each quarter (Row 6 - light yellow) in order to calculate the percent of match accrued (Row 7). The “Initial” column indicates that no match funds have been accrued prior to the contract execution date, and the “Final” column indicates that by the end of 12 quarters, 100 percent of the match commitment will be met. Please note that the match dollar amount must be entered manually into each cell in Row 6 in order for the formulas in Row 7 to automatically calculate the percent accrued.
(4) Contract Execution: This section has already been completed in the Template, and should remain as is.
(5) Tasks: Applicants may need to adjust the Task numbers (#1, #2, #3, etc,) according to the number of Tasks in the actual project application. All required Operations & Maintenance Tasks described for BMP implementation projects in the FY2024 Grant Guidelines are provided as Tasks #5, #8, and #11 in the Schedule Template and should be included as appropriate to the project. Access the Guidelines document at the GAEPD Grants web page: https://epd.georgia.gov/outreach/grants/section-319h-georgias-nonpoint-source-implementation-grant. It may be necessary to shorten the Task title in the Project Schedule to fit within the allotted space, but the intent of the Task should remain clear. Applicants should “color-in” the appropriate number of cells, creating a line that depicts the expected length of each Task in months. Tasks that will require less than one month should be represented by filling in an entire month's cell. Applicants are encouraged to color code their tasks by suitable categories. For instance, in the “Example Schedule”, Meetings & Outreach are color coded in purple and Tasks related to Urban BMPs are color coded in orange. Applicants should provide a color key for the selected color codes.
(6) Federal/State Reporting Requirements: 319(h) Grant recipients are required to submit Quarterly Reports and Invoices every three months for the length of the project to ensure adherence to the Project Schedule and to proactively address any concerns in a timely manner. These reporting requirement Tasks have already been completed in the Template (color coded in pink) and should remain as they are.
(7) Contract Close-Out: This Task has already been completed in the Project Schedule Template, and should remain as is. The contract close-out date can be readjusted as necessary once grant funds are awarded.

## Example Schedule - Do Not Use
Project Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | 7th Quarter |  |  | 8th Quarter |  |  | 9th Quarter |  |  | 10th Quarter |  |  | 11th Quarter |  |  | 12th Quarter |  |  | Final
Federal Drawdown Amount | 209877 | 5000 |  |  | 5000 |  |  | 10000 |  |  | 10000 |  |  | 10000 |  |  | 15000 |  |  | 15000 |  |  | 40000 |  |  | 40000 |  |  | 20000 |  |  | 18889 |  |  | 20988 |  |  | 0
Percent Federal Remaining | 100% | 97.62% |  |  | 95.24% |  |  | 90.47% |  |  | 85.71% |  |  | 80.94% |  |  | 73.79% |  |  | 66.65% |  |  | 47.59% |  |  | 28.53% |  |  | 19% |  |  | 10% |  |  | -4.163e-15% |  |  | 0%
Match Amount | 0 | 3333 |  |  | 3333 |  |  | 6667 |  |  | 6667 |  |  | 6667 |  |  | 10000 |  |  | 10000 |  |  | 26667 |  |  | 26667 |  |  | 13332 |  |  | 12593 |  |  | 13992 |  |  | 139918
Percent Match Accrued | 0% | 2.382% |  |  | 4.764% |  |  | 9.529% |  |  | 14.29% |  |  | 19.06% |  |  | 26.21% |  |  | 33.35% |  |  | 52.41% |  |  | 71.47% |  |  | 81% |  |  | 90% |  |  | 100% |  |  | 100%
|  | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01
Milestones/Tasks
Execute Contract | bar: 2023-10-01
Task 1: Introduce Project to Watershed Partners | bar: 2023-12-01 to 2024-01-01
Task 2: Convene 3 Meetings to Assign Implementation Responsibilities | bar: 2024-03-01 to 2024-04-01; 2024-06-01 to 2024-07-01; 2024-09-01 to 2024-10-01
Task 3: Recruit & Contract with Ag Producers for Ag BMPs | bar: 2024-04-01 to 2025-09-01; 2026-01-01 to 2026-03-01
Task 4: Install Ag BMPs | bar: 2024-10-01 to 2026-06-01
Task 5: Operations and Maintenance of Agricultural BMPs | bar: 2024-10-01 to 2026-09-01
Task 6: Recruit & Contract with Property Owners for Septic BMPs | bar: 2024-04-01 to 2025-09-01; 2026-01-01 to 2026-03-01
Task 7: Pump Out, Repair or Replace Septic Systems | bar: 2024-10-01 to 2026-06-01
Task 8: Education for Operations and Maintenance of Septic Systems | bar: 2024-10-01 to 2026-09-01
Task 9: Recruit & Contract with Local Gov, Biz, or Institution for Urban BMP | bar: 2024-04-01 to 2025-09-01
Task 10: Install Green Infrastructure stormwater BMPs in Urban Watershed | bar: 2024-10-01 to 2026-06-01
Task 11: Operations and Maintenance of Urban and GI/LID BMPs | bar: 2024-10-01 to 2026-09-01
Task 12: Conduct 2 BMP Workshops or Field Days | bar: 2025-06-01 to 2025-08-01; 2026-02-01 to 2026-04-01
Task 13: Identification of Documents and Projects | bar: 2026-04-01
Task 14: Estimate load reductions using online PLET or other acceptable models | bar: 2025-01-01; 2025-04-01; 2025-07-01; 2025-10-01; 2026-01-01; 2026-04-01; 2026-07-01
Task 15: Prepare and submit Quarterly Invoices & Status Reports | bar: 2024-01-01; 2024-04-01; 2024-07-01; 2024-10-01; 2025-01-01; 2025-04-01; 2025-07-01; 2025-10-01; 2026-01-01; 2026-04-01; 2026-07-01
Task 16: Participate in project review meetings with GAEPD | bar: 2024-04-01; 2025-04-01; 2026-04-01
Task 17: Submit Final Invoice and Closeout Report
Key
Meetings & Outreach
Ag BMPs
Septic BMPs
Urban BMPs
Contract & Reports

## Project Schedule Template
Grant Project Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | 7th Quarter |  |  | 8th Quarter |  |  | 9th Quarter |  |  | 10th Quarter |  |  | 11th Quarter |  |  | 12th Quarter |  |  | Final
Federal Drawdown Amount | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Percent Federal Remaining | 100% | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0!
Match Amount | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Percent Match Accrued | 0% | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0!
|  | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01
Milestones/Tasks
Execute Contract | bar: 2024-07-01
Task 1:
Task 2:
Task 3:
Task 4:
Task 5:
Task 6:
Task 7:
Task 8:
Task 9:
Task 10:
Task 11:
Task 12:
Task 13:
Task 14:
Task 15:
Task 16:
Task 17:
Task 18:
Task 19:
Task 20:
Task 21:
Task 22: Identification of Documents and Projects | bar: 2027-01-01
Task 23: Estimate load reductions using online PLET or other acceptable models | bar: 2025-10-01; 2026-01-01; 2026-04-01; 2026-07-01; 2026-10-01; 2027-01-01; 2027-04-01
Task 24: Prepare and submit Quarterly Invoices & Status Reports | bar: 2024-10-01; 2025-01-01; 2025-04-01; 2025-07-01; 2025-10-01; 2026-01-01; 2026-04-01; 2026-07-01; 2026-10-01; 2027-01-01; 2027-04-01
Task 25: Participate in project review meetings with GAEPD | bar: 2025-01-01; 2026-01-01; 2027-01-01
Task 26: Submit Final Invoice and Closeout Report
Key
Contract & Reports