## Instructions
(1) Project Timeline (Row 2): Grant projects are limited to 30 months in length. For the purposes of the application, all applicants should base their timeline on an January 2027 start date. Once grant funds are awarded, the Schedule can be reconfigured based on actual start and end dates. The Schedule is divided into quarters.
(2) Grant Drawdown (Rows 3 & 4): Applicants must estimate the amount of Grant funds they will spend each quarter as well as the remaining grant fund percentage. The “Initial” column indicates that no grant funds can be expended prior to the contract execution date, and the “Final” column indicates that by the end, all grants funds are expected to be spent. Please note that the both the grant dollar amount (Row 3) and the percentage remaining (Row 4) must be entered manually into each cell.
(3) Match Expenditures (Rows 6 & 7 and 9 & 10): Applicants must also estimate the rate at which they expect to accrue match dollars. The “Initial” column indicates that no match funds can be accrued prior to the contract execution date, and the “Final” column indicates that by the end, 100 percent of the match commitment will be met. Please note that both the match dollar amount (Row 6) and the percentage accrued (Row 7) must be entered manually into each cell.
(4) Contract Execution: This section has already been completed in the Template, and should remain as is.
(5) Tasks: Applicants should include all tasks from Section 5. (Project Activites) Task numbers should remain the same. It may be appropriate to shorten the task title to fit within the allotted space, but the intent of the task should remain clear. Applicants should “fill-in” the appropriate number of cells, creating a line that depicts the expected length of each task in months (tasks that will require less than one month should be represented by the filling in of an entire cell). Applicants are encouraged to color code their tasks by suitable categories. For instance, in the “Example Schedule”, meetings are color coded in purple and tasks that will result in deliverables to GAEPD are color coded in orange. A key should be provided.
(6) State Reporting Requirements: Grant recipients are required to submit Quarterly Reports and Invoices every three months for the length of the project to ensure adherence to the Implementation and Drawdown Schedule and to proactively address any concerns in a timely manner. These reporting requirements have already been completed in the Template (color coded in pink) and should remain as they are.
(7) Contract Close-Out: This section has already been completed in the Template, and should remain as is. The contract close-out date can be readjusted as necessary once grant funds are awarded.

## Example
Appendix B: Project Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | Final
Grant Drawdown Amount | 0 | 16666.67 |  |  | 16666.67 |  |  | 16666.67 |  |  | 16666.67 |  |  | 16666.67 |  |  | 16666.67 |  |  | 100000
Percent Federal Remaining | 100% | 83.33% |  |  | 66.67% |  |  | 50% |  |  | 33.33% |  |  | 16.67% |  |  | -2e-05% |  |  | 0%
Match Amount | 0 | 1666.67 |  |  | 1666.67 |  |  | 1666.67 |  |  | 1666.67 |  |  | 1666.67 |  |  | 1666.67 |  |  | 10000
Percent Match Accrued | 0% | 16.67% |  |  | 33.33% |  |  | 50% |  |  | 66.67% |  |  | 83.33% |  |  | 100% |  |  | 100%
|  | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01
Milestones/Tasks
Execute Contract
Task 1: | bar: 2026-01-01 to 2026-03-01
Task 2: | bar: 2026-04-01
Task 3: | bar: 2026-05-01 to 2026-06-01
Task 4: Conduct Public Meeting | bar: 2026-06-01
Task 5: | bar: 2026-07-01 to 2026-08-01
Task 6: | bar: 2026-09-01 to 2026-10-01
Task 7: | bar: 2026-11-01 to 2027-04-01
Task 8: Conduct Public Outreach Day | bar: 2027-05-01
Task 9: Submit Monitoring Data | bar: 2027-06-01
Submit Quarterly Invoices & Status Reports | bar: 2026-04-01; 2026-07-01; 2026-10-01; 2027-01-01; 2027-04-01
Submit Final Close-Out Report

## Template
Appendix B: SFY2027 Regional Water Plan Grant Project Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | 7th Quarter |  |  | 8th Quarter |  |  | 9th Quarter |  |  | 10th Quarter |  |  | Final
Grant Drawdown Amount | 0 | 15000 |  |  | 15000 |  |  | 15000 |  |  | 15000 |  |  | 15000 |  |  | 15000 |  |  | 15000 |  |  | 15000 |  |  | 15000 |  |  | 15000 |  |  | 150000
Percent Seed Remaining | 100% | 90% |  |  | 80% |  |  | 70% |  |  | 60% |  |  | 50% |  |  | 40% |  |  | 30% |  |  | 20% |  |  | 10% |  |  | 1.388e-14% |  |  | 0%
Match Amount | 0 | 1500 |  |  | 1500 |  |  | 1500 |  |  | 1500 |  |  | 1500 |  |  | 1500 |  |  | 1500 |  |  | 1500 |  |  | 1500 |  |  | 1500 |  |  | 15000
Percent Match Accrued | 0% | 10% |  |  | 20% |  |  | 30% |  |  | 40% |  |  | 50% |  |  | 60% |  |  | 70% |  |  | 80% |  |  | 90% |  |  | 100% |  |  | 100%
|  | Jan 2027 | Feb 2027 | Mar 2027 | Apr 2027 | May 2027 | Jun 2027 | Jul 2027 | Aug 2027 | Sep 2027 | Oct 2027 | Nov 2027 | Dec 2027 | Jan 2028 | Feb 2028 | Mar 2028 | Apr 2028 | May 2028 | Jun 2028 | Jul 2028 | Aug 2028 | Sep 2028 | Oct 2028 | Nov 2028 | Dec 2028 | Jan 2029 | Feb 2029 | Mar 2029 | Apr 2029 | May 2029 | Jun 2029
Milestones/Tasks
Execute Contract
Task 1:
Task 2:
Task 3:
Task 4:
Task 5:
Task 6:
Task 7:
Task 8:
Submit Quarterly Invoices & Status Reports
Submit Final Close-Out Report