## Instructions
(1) Project Timeline (Row 2): 319(h) projects are limited to 3 years in length. The Schedule Template assumes awarded projects will be contracted in October 2022 and be completed by September 2025. For the purposes of the application, all applicants MUST base their timeline on an October 2022 start date. If a proposed project is expected to be completed prior to September 2024, the remaining columns should be left blank. Once grant funds are awarded, the Schedule can be reconfigured based on actual start and end dates. The Schedule is divided into quarters that are numbered sequentially in order to track activities for the entire term of the project.
(2) Federal Drawdown Amount & Percent Federal Remaining (Rows 3 & 4): Applicants MUST estimate the amount of 319(h) Grant federal funds that they will spend each quarter (Row 3 - light blue) in order to calculate the percent of federal funds remaining (Row 4). The “Initial” column indicates the total amount of grant funds to be expended and the “Final” column indicates that by the end of 12 quarters all grant funds have been spent, resulting in $0 remaining. Please note that the grant dollar amount must be entered manually into each cell in Row 3 in order for the formulas in Row 4 to automatically calculate the percent remaining.
(3) Match Amount & Percent Match Accrued (Rows 6 & 7): Applicants must also estimate the match in dollar amounts that they expect to accrue each quarter (Row 6 - light yellow) in order to calculate the percent of match accrued (Row 7). The “Initial” column indicates that no match funds have been accrued prior to the contract execution date, and the “Final” column indicates that by the end of 12 quarters, 100 percent of the match commitment will be met. Please note that the match dollar amount must be entered manually into each cell in Row 6 in order for the formulas in Row 7 to automatically calculate the percent accrued.
(4) Contract Execution: This section has already been completed in the Template, and should remain as is.
(5) Tasks: Applicants should include all tasks listed on page 11 of the FY2022 Grant Guidelines at https://epd.georgia.gov/document/document/final-section-319h-fy2022-grant-guidelines/download. Task numbers should remain the same. It may be appropriate to shorten the task title to fit within the allotted space, but the intent of the task should remain clear. Applicants should “fill-in” the appropriate number of cells, creating a line that depicts the expected length of each task in months (tasks that will require less than one month should be represented by the filling in of an entire cell). Applicants are encouraged to color code their tasks by suitable categories. For instance, in the “Example Schedule”, Meetings & Outreach are color coded in purple and tasks related to Urban BMPs are color coded in orange. A key should be provided.
(6) Federal/State Reporting Requirements: 319(h) Grant recipients are required to submit Quarterly Reports and Invoices every three months for the length of the project to ensure adherence to the Project Schedule and to proactively address any concerns in a timely manner. These reporting requirements have already been completed in the Template (color coded in pink) and should remain as they are.
(7) Contract Close-Out: This section has already been completed in the Template, and should remain as is. The contract close-out date can be readjusted as necessary once grant funds are awarded.

## Example Schedule
Project Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | 7th Quarter |  |  | 8th Quarter |  |  | 9th Quarter |  |  | 10th Quarter |  |  | 11th Quarter |  |  | 12th Quarter |  |  | Final
Federal Drawdown Amount | 209877 | 5000 |  |  | 5000 |  |  | 10000 |  |  | 10000 |  |  | 10000 |  |  | 15000 |  |  | 15000 |  |  | 40000 |  |  | 40000 |  |  | 20000 |  |  | 18889 |  |  | 20988 |  |  | 0
Percent Federal Remaining | 100% | 97.62% |  |  | 95.24% |  |  | 90.47% |  |  | 85.71% |  |  | 80.94% |  |  | 73.79% |  |  | 66.65% |  |  | 47.59% |  |  | 28.53% |  |  | 19% |  |  | 10% |  |  | -4.163e-15% |  |  | 0%
Match Amount | 0 | 3333 |  |  | 3333 |  |  | 6667 |  |  | 6667 |  |  | 6667 |  |  | 10000 |  |  | 10000 |  |  | 26667 |  |  | 26667 |  |  | 22107 |  |  | 12593 |  |  | 13992 |  |  | 148693
Percent Match Accrued | 0% | 2.242% |  |  | 4.483% |  |  | 8.967% |  |  | 13.45% |  |  | 17.93% |  |  | 24.66% |  |  | 31.38% |  |  | 49.32% |  |  | 67.25% |  |  | 82.12% |  |  | 90.59% |  |  | 100% |  |  | 100%
|  | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01
Milestones/Tasks
Execute Contract | bar: 2022-10-01
Task 1: Introduce Project to Watershed Partners | bar: 2022-12-01 to 2023-01-01
Task 2: Convene 3 Meetings to Assign Implementation Responsibilities | bar: 2023-03-01 to 2023-04-01; 2023-06-01 to 2023-07-01; 2023-09-01 to 2023-10-01
Task 3: Recruit & Contract with Ag Producers for Ag BMPs | bar: 2023-04-01 to 2024-09-01; 2025-01-01 to 2025-03-01
Task 4: Install Ag BMPs | bar: 2023-10-01 to 2025-06-01
Task 5: Operations and Maintenance of Agricultural BMPs | bar: 2023-10-01 to 2025-09-01
Task 6: Recruit & Contract with Property Owners for Septic BMPs | bar: 2023-04-01 to 2024-09-01; 2025-01-01 to 2025-03-01
Task 7: Pump Out, Repair or Replace Septic Systems | bar: 2023-10-01 to 2025-06-01
Task 8: Education for Operations and Maintenance of Septic Systems | bar: 2023-10-01 to 2025-09-01
Task 9: Recruit & Contract with Local Gov, Biz, or Institution for Urban BMP | bar: 2023-04-01 to 2024-09-01
Task 10: Install Green Infrastructure stormwater BMPs in Urban Watershed | bar: 2023-10-01 to 2025-06-01
Task 11: Operations and Maintenance of Urban and GI/LID BMPs | bar: 2023-10-01 to 2025-09-01
Task 12: Conduct 2 BMP Workshops or Field Days | bar: 2024-06-01 to 2024-08-01; 2025-02-01 to 2025-04-01
Task 13: Identification of Documents and Projects | bar: 2025-04-01
Task 14: Estimate load reductions using STEPL or other acceptable models | bar: 2024-01-01; 2024-04-01; 2024-07-01; 2024-10-01; 2025-01-01; 2025-04-01; 2025-07-01
Task 15: Prepare and submit Quarterly Invoices & Status Reports | bar: 2023-01-01; 2023-04-01; 2023-07-01; 2023-10-01; 2024-01-01; 2024-04-01; 2024-07-01; 2024-10-01; 2025-01-01; 2025-04-01; 2025-07-01
Task 16: Participate in project review meetings with GAEPD | bar: 2023-04-01; 2024-04-01; 2025-04-01
Task 17: Submit Final Invoice and Closeout Report
Key
Meetings & Outreach
Ag BMPs
Septic BMPs
Urban BMPs
Contract & Reports

## Schedule Template
10. Project Schedule
| Initial | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | 5th Quarter |  |  | 6th Quarter |  |  | 7th Quarter |  |  | 8th Quarter |  |  | 9th Quarter |  |  | 10th Quarter |  |  | 11th Quarter |  |  | 12th Quarter |  |  | Final
Federal Drawdown Amount | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Percent Federal Remaining | 100% | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | 0%
Match Amount | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Percent Match Accrued | 0% | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | 100%
|  | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01
Milestones/Tasks
Execute Contract | bar: 2022-10-01
Task 1:
Task 2:
Task 3:
Task 4:
Task 5: Operations and Maintenance of Agricultural BMPs
Task 6:
Task 7:
Task 8: Education for Operations and Maintenance of Septic Systems
Task 9:
Task 10:
Task 11: Operations and Maintenance of Urban and GI/LID BMPs
Task 12:
Task 13:
Task 14:
Task 15:
Task 16:
Task 17:
Task 18:
Task 19:
Task 20:
Task 21:
Task 22: Identification of Documents and Projects | bar: 2025-04-01
Task 23: Estimate load reductions using STEPL or other acceptable models | bar: 2024-01-01; 2024-04-01; 2024-07-01; 2024-10-01; 2025-01-01; 2025-04-01; 2025-07-01
Task 24: Prepare and submit Quarterly Invoices & Status Reports | bar: 2023-01-01; 2023-04-01; 2023-07-01; 2023-10-01; 2024-01-01; 2024-04-01; 2024-07-01; 2024-10-01; 2025-01-01; 2025-04-01; 2025-07-01
Task 25: Participate in project review meetings with GAEPD | bar: 2023-04-01; 2024-04-01; 2025-04-01
Task 26: Submit Final Invoice and Closeout Report
Key
Meetings & Outreach
Ag BMPs
Septic BMPs
Urban BMPs
Contract & Reports